## Resource_Based_Estimation_-_2 (hidden)
Resource Estimation | [5 empty] | Design |  |  |  | Development | [6 empty] | Testing |  |  | UAT |  | Deployment | Support |  | Totals
Role | Daily Rate | Total Days | Total Cost | Job |  | 2009-01-05 | 2009-01-12 | 2009-01-19 | 2009-01-26 | 2009-02-02 | 2009-02-09 | 2009-02-16 | 2009-02-23 | 2009-03-02 | 2009-03-09 | 2009-03-16 | 2009-03-23 | 2009-03-30 | 2009-04-06 | 2009-04-13 | 2009-04-20 | 2009-04-27 | 2009-05-04 | 2009-05-11
Engagement Manager | 50000 | 0 | 825000 | Overall Engagement management & cust sat |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 16.5
Project manager | 50000 | 0 | 3350000 | Project management |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 67
Architect | 50000 | 0 | 800000 | Design and Architecture Activities |  | 2009-01-05: 2; 2009-01-12: 2; 2009-01-19: 2; 2009-01-26: 2; 2009-03-09: 2; 2009-03-16: 2; 2009-03-23: 2; 2009-03-30: 2 | 16
Consultant | 50000 | 0 | 4500000 | Technical consulting (Integration/MDM) |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 90
Consultant | 50000 | 0 | 1000000 | MDM SME |  | 2009-01-05: 5; 2009-01-12: 5; 2009-01-19: 5; 2009-01-26: 5 | 20
Consultant | 50000 | 0 | 1750000 | Test lead |  | 2009-02-23: 5; 2009-03-02: 5; 2009-03-09: 5; 2009-03-16: 5; 2009-03-23: 5; 2009-03-30: 5; 2009-04-06: 5 | 35
Developer |  | 0 | 0 | Partner Dev lead |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 90
Developer |  | 0 | 0 | Development of code |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 90
Developer |  | 0 | 0 | Development of code |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 70
Developer |  | 0 | 0 | Development of code |  | 2009-01-26: 5; 2009-02-02: 5; 2009-02-09: 5; 2009-02-16: 5; 2009-02-23: 5; 2009-03-02: 5; 2009-03-09: 5; 2009-03-16: 5; 2009-03-23: 5; 2009-03-30: 5; 2009-04-06: 5 | 55
Developer |  | 0 | 0 | Development of code |  | 2009-02-02: 5; 2009-02-09: 5; 2009-02-16: 5; 2009-02-23: 5; 2009-03-02: 5; 2009-03-09: 5; 2009-03-16: 5 | 35
Tester |  | 0 | 0 | Testing |  | 2009-03-02: 5; 2009-03-09: 5; 2009-03-16: 5; 2009-03-23: 5; 2009-03-30: 5; 2009-04-06: 5; 2009-04-13: 5; 2009-04-20: 5 | 40
Tester |  | 0 | 0 | Testing |  | 2009-03-02: 5; 2009-03-09: 5; 2009-03-16: 5; 2009-03-23: 5; 2009-03-30: 5; 2009-04-06: 5 | 30
sub-totals | [24 empty] | 654.5
Man-days |  |  |  | Total Man-days | 654.5
|  |  |  | Planning Stage | 0
|  |  |  | Dev and Stabilisation Stage | 0
12225000 |  |  |  | Total Cost for MS Dev
Project Start Date |  | 2009-01-05
USD rate | 50 |  |  | 244500
|  | USD | INR
Architect rate
Consultant rate
partner resource / man month
per day rate |  |  | 0
Number of working days in a month |  |  | 20
Productivity Multiple |  | 80%
Stabilisation Multiple |  | 50%
Note on A2: Basic skill category that the resource will require.
Note on B2: Type in the Daily Rate for the price of this resource to affect the total cost.
Note on C2: Total Days needed for this resource. This is the sum of the calendar to the right.
Note on D2: The Total Cost is the Total number of days worked by the resource times the Daily Rate
Note on E2: Job that the resource will perform on the solution.
Note on A31: Percent of a day that an average team member is productive. Average should be around 80%.
Note on A32: Amount of time that should be added to the development time to stabilise the code. An average quality solution should have 50% stabilisation.

## Detail (hidden)
Process Steps | Site Collection, Sites & Sub Sites | Data Lists / Document Libraries / View | Integration |  | Workflows | Web Parts | Cutomisation / Buss.Logic |  | Reports
New Case Registration form | Y | Y | Y | 3 |  |  | Y | High
Associate with Previous Case for the same Customer |  | Y |  |  |  | Y | Y | High
Open the Case | Y | Y | Y | 2 |  |  | Y | High
Open Associated Case in Detail | Y |  | Y |  |  |  | Y
Functionality for Locking & Unlocking Case | [6 empty] | Y
Get / Read History | Y | Y | Y |  | Y |  | Y
Check Point form with Notes | Y | Y | Y | 1 |  |  | Y | High
Status Entry form | Y | Y | Y | 1 |  |  | Y
Management information reporting leader tool (3 Reports) | [6 empty] | Y
Search | Y
Security & Permissions | Y

## ProjectEstimation
PROJECT ESTIMATION
Project Name | Client Name
ShoppingList
Project Start Date
Project End Date
Project Duration
Activities |  | % | Total Man Days | Total man Hours | Comment
Effort |  |  | 66 | 528
Plan |  | 4% | 2 | 16 | Accounted in Effort sheet
Design/ Development |  | 81% | 54 | 432 | Accounted in Effort sheet
Testing |  | 15% | 10 | 80 | Accounted in Effort sheet
Total Effort |  | 100% | 66 | 528

## Effort
S.No. | Development Phase | Features & Functionalities | Nos. | Complexity | Effort Days (Normal Complexity) | Total Man Days | Total days (Phase Wise) | Deliverables
| Plan | [5 empty] | 2
|  | Detailed Requirement Gathering/ Project Understanding | 1 | 1 | 2 | 2
| Design/ Development | [5 empty] | 54
| Localization | Implement language localization to support both language english and norwegian. | 1 | 1 | 1 | 1
| Splash Screen | Creation of splash effect and app architecture with below tabbars. | 1 | 1 | 1 | 1
| Front Page | 1. Fetching latest and popular recipes data from webservices and parse the xml. 2.Work on creation of UI and populate the data on UI. 3. Work on handling horizontal or vertical pagewise browsing of recipes. 4. Work on handling asynchronous downloading images of recipes while scrolling table. 5. Work on creation of horizontal screen to show all receipes with their rating and title. | 1 | 2 | 4 | 8
| News | 1. Work on New home page. Downloading data from webservice parse the xml and populate the data on UI. 2. Work on Article List screen . Downloading data from webservice parse the xml and populate the data on UI. 3. Work on Article Detail screen . Downloading data from webservice parse the xml and populate the data on UI with related recipes. | 1 | 2 | 3.5 | 7
| Recipe Detail | 1. Work on showing Recipe detail screen with Recipe,Guide and related recipe tabs. Downloading data from webservice parse the xml and populate the data on UI with related recipes. 2. Implement feature of adding recipe to cookbook, shopping list and share | 1 | 2 | 4.5 | 9
| Cookbook | 1. Work on Cookbook Login screen using webservice and add logic for user authentication. 2. Work on Cookbook Create Account screen using webservice. 3. Work on cookbook recipe listing screens to list all recipies with edit feature. 4. Integrate recipe listing page with recipe detail page. | 1 | 2 | 3.5 | 7
| Shopping List | 1. Fetch recipe data and add it to shopping list. Add features of adding new shopping list item, remove all items, remove single item, checkmark item and place it in physical shopping basket, Feature of adding badge number. 2. For this we have to create local db to maintain shopping list items and total it based on added recipes and to make shopping list persist between application usage. | 1 | 2 | 4.5 | 9
| Sharing | 1. Work on integration emails. 2. Work on integrating facebook framework 3. Work on sending sms. | 1 | 2 | 2.5 | 5
| Search | 1. Work on search feature and listing categories on home search screen . 2. Work on search feature and listing corresponding subcategories on search screen . 3. Work on creating recipies listing screen with search feature and link it with recipe detail screen. | 1 | 2 | 3.5 | 7
| Build / Test | [5 empty] | 10
|  | Unit Testing On Simulator / Device / QC | 1 | 1 | 10 | 10
|  | Total |  |  |  | 66 | 66

## Assumptions
Assumptions
1. Database will be already exist on server.
2. Web service or API to communicate with database will be already developed and provided to us. We are assuming that all API communication messages will be in xml format.
3. Assuming application will support both languages english and norwegian.
4. Assuming all screens will be shown in portrait mode except one recipe sceen which is mention in given PDF document.
5. We are assuming that all required sliced images for tab bar, splash screen, label , button background images etc or psd file will be given to us by client.

## Query
Queries
1. It seems that Front page does not belong to any tab bar. In tab bar based application each screen should belong to any tab bar. So I guess we can add one more tab bar below 'Home' to show front page. Please confirm.
2. In Front page horizontal screen, do we nedd to show corresponding images as well ? We are assuming that image urls will be provided to us in response xml of api and all images will be in same dimension and format.
3. In this application in all screens where we are listing recipies , do we need to use horizontal or vertical paging if recipe amount grows large ? If yes then is our existing rest based web service is capable to provide only pagewise data to maintain the speed of browsing the application ? or webservice provide all recipe data at once ?